## Worksheet
Education Planning - Project Timeline (Analysis View)
Phase | Activity | Start Date | End Date | Duration (Days) | Status | Budget (USD)(Est.)
Phase 1: Needs Assessment & Goal Setting
1.1 | Stakeholder Consultation | 2024-03-01 | 2024-03-15 | 15 | Completed | $8,500(Actual)
1.2 | Educational Needs Analysis | 2024-03-16 | 2024-04-15 | 30 | In Progress | $15,750(Est.)
Phase 2: Curriculum & Resource Development
2.1 | Curriculum Design Workshop | 2024-04-16 | 2024-05-31 | 46 | Planned | $38,500(Est.)
2.2 | Learning Material Development | 2024-06-01 | 2024-08-31 | 92 | Planned | $75,300(Est.)
Phase 3: Implementation & Pilot Testing
3.1 | Pilot Program Launch (5 Schools) | 2024-09-01 | 2024-11-30 | 91 | Planned | $68,950(Est.)
Phase 4: Evaluation & Scaling Strategy
4.1 | Data Collection & Impact Assessment | 2024-12-01 | 2025-03-31 | 121 | Planned | $45,675(Est.)
Phase 5: Final Reporting & Knowledge Sharing
5.1 | Comprehensive Evaluation Report | 2025-04-01 | 2025-06-30 | 91 | Delayed (Pending Pilot Feedback) | $23,450(Est.)
Total Estimated Budget: | [5 empty] | $275,125(Projected)
Overall Progress: | [5 empty] | 38%
Legend:
Completed- Task has been finalized.
In Progress- Work is currently underway.
Planned- Scheduled for future execution.
Delayed- Progress is behind schedule.