## Worksheet
Education Planning Project Timeline
Phase | Task Description | Start Date | End Date | Status | Responsible Party
Planning & Initiation | Define project scope and objectives | 2024-01-15 | 2024-01-31 | Completed | Laura Smith (Project Manager)
Needs Assessment | Evaluate student learning requirements and resources | 2024-02-01 | 2024-02-15 | Completed | Dr. James Reed (Curriculum Lead)
Curriculum Design | Develop course modules and learning outcomes | 2024-02-16 | 2024-03-15 | In Progress | Sarah Lin (Instructional Designer)
Resource Allocation | Secure teaching materials and technology tools | 2024-03-16 | 2024-03-31 | In Progress | Tony Kim (Logistics Coordinator)
Faculty Training | Conduct professional development sessions for instructors | 2024-04-01 | 2024-04-15 | Delayed | Maria Gonzalez (HR & Training)
Student Onboarding | Enroll students and distribute learning kits | 2024-04-16 | 2024-05-31 | Delayed | Laura Smith (Project Manager)
Implementation Phase | Launch full program rollout and monitoring | 2024-06-01 | 2024-11-30 | Delayed | All Departments (Collaborative)
Evaluation & Feedback | Collect and analyze program feedback from stakeholders | 2024-12-01 | 2025-01-31 | Delayed | Laura Smith & Dr. James Reed (Evaluation Team)