## Worksheet
Phase | Task Description | Start Date | End Date | Status
Planning & Research | Evaluate educational goals and requirements | 2023-10-01 | 2023-10-15 | In Progress
Course Selection | Select appropriate courses and programs | 2023-10-16 | 2023-10-31 | Pending
Application Preparation | Prepare application materials and documents | 2023-11-01 | 2023-11-20 | Pending
Application Submission | Submit applications to institutions | 2023-11-21 | 2023-12-05 | Pending
Admissions Review | Wait for acceptance decisions from institutions | 2023-12-06 | 2024-01-15 | Pending
Decision & Enrollment | Select institution and confirm enrollment | 2024-01-16 | 2024-01-31 | Pending
Preparation & Logistics | Arrange housing, visas, and travel plans | 2024-02-01 | 2024-03-15 | Pending
Orientation & Start Date | Attend orientation and begin studies | 2024-03-16 | 2024-03-16 | Pending