## Worksheet
Education Planning - Project Timeline Dashboard
Track key milestones, deadlines, and progress for academic planning initiatives
Phase / Milestone | Start Date | End Date | Status | Responsible Team | Description
Needs Assessment & Planning Phase | 2024-01-15 | 2024-03-31 | Completed | Planning Committee | Evaluate current programs, identify learning gaps, and define objectives.
Curriculum Development | 2024-04-01 | 2024-08-31 | In Progress | Instructional Design Team | Create new course materials aligned with learning outcomes.
Faculty Training & Onboarding | 2024-09-01 | 2024-10-15 | In Progress | Training Department | Prepare educators for new curriculum implementation.
Student Enrollment & Registration | 2024-10-16 | 2024-11-30 | In Progress | Admissions Office | Open enrollment window for new academic programs.
Program Launch & Rollout | 2024-12-01 | 2025-01-31 | Delayed | All Departments | Full implementation of revised curriculum across all academic levels.
Mid-Year Review & Evaluation | 2025-02-15 | 2025-03-31 | Completed | Evaluation Committee | Analyze student performance and feedback for continuous improvement.
Project Completion:65% ¦On Track:3/5 milestones ¦Risk Level:Moderate