## Worksheet
Education Planning Project Timeline
Phase | Task / Activity | Start Date | End Date | Responsible Team | Status
Phase 1: Planning & Assessment | Initial project setup, needs assessment, and goal definition
1.1 | Stakeholder Engagement & Needs Analysis | 2024-09-01 | 2024-09-15 | Educational Consultants, Admin Team | In Progress
1.2 | Curriculum Review & Gap Analysis | 2024-09-16 | 2024-09-30 | Academic Department, Subject Leads | Pending
Phase 2: Development & Design | Curriculum development, resource creation, and program design
2.1 | Design Learning Objectives & Outcomes | 2024-10-01 | 2024-10-15 | Curriculum Design Team, Instructional Coaches | Pending
2.2 | Develop Lesson Plans & Materials (Pilot Modules) | 2024-10-16 | 2024-11-30 | Teachers, Content Developers | Pending
Phase 3: Implementation & Rollout | Pilot testing, training, and full program launch
3.1 | Pilot Program Launch (Grade 9 - 2 Classes) | 2024-12-01 | 2025-01-31 | Teachers, Instructional Coaches, IT Support | Pending
3.2 | Facilitate Teacher Training & Workshops | 2024-12-05 | 2024-12-15 | Professional Development Team, External Trainers | Pending
Phase 4: Evaluation & Continuous Improvement | Assessment, feedback collection, and refinement
4.1 | Collect Student & Teacher Feedback (Pilot) | 2025-01-15 | 2025-01-31 | Evaluation Team, Data Analysts | Pending
4.2 | Analyze Performance & Adjust Curriculum (Based on Feedback) | 2025-02-01 | 2025-03-15 | Curriculum Design Team, Academic Leads | Pending
Phase 5: Full Rollout & Sustainability Planning | Institution-wide deployment and long-term strategy development
5.1 | Full Program Rollout (All Grades 9-12) | 2025-03-16 | 2025-07-31 | All Teaching Staff, Admin Team | Pending
5.2 | Sustainability & Long-Term Planning Meeting | 2025-08-01 | 2025-08-15 | Leadership Team, Finance, Curriculum Council | Pending
Total Project Duration: |  | September 1, 2024 – August 15, 2025 |  |  | Completed
Last Updated:June 4, 2024 ¦ Project Version: v1.2 ¦ Status: On Track