## Worksheet
Education Planning - Project Timeline (Employee View)
Task | Description | Start Date | End Date | Status | Assigned To
Needs Assessment Survey | Circulate survey to identify education needs across departments. | 2024-04-01 | 2024-04-15 | In Progress | John Doe
Curriculum Development | Create structured learning modules based on survey results. | 2024-04-16 | 2024-05-10 | Pending | Alice Smith
Faculty Recruitment | Hire qualified trainers and subject matter experts. | 2024-05-01 | 2024-05-15 | Pending | Robert Brown
Course Launch Preparation | Finalize schedules, materials, and digital platforms. | 2024-05-16 | 2024-05-31 | Pending | Sarah Wilson
Phase 1 Training - Leadership Skills | Conduct first round of training sessions for mid-level managers. | 2024-06-01 | 2024-06-30 | Pending | All Department Heads
Feedback Collection & Review | Gather participant feedback and evaluate training effectiveness. | 2024-07-01 | 2024-07-15 | Pending | Lisa Garcia
Curriculum Enhancement Workshop | Update course content based on feedback and performance data. | 2024-07-16 | 2024-07-31 | Pending | All Trainers
Phase 2 Training - Technical Skills | Roll out advanced technical training for IT and engineering teams. | 2024-08-01 | 2024-09-30 | Pending | IT & Engineering Staff
Final Evaluation Report | Compile results, ROI analysis, and recommendations for next cycle. | 2024-10-01 | 2024-10-15 | Pending | Project Lead Team