## Worksheet
Education Planning - Project Timeline (Extended)
Phase | Task Description | Start Date | End Date | Status | Responsible Party | Budget (USD)
Phase 1: Needs Assessment | Conduct student needs and skill gap analysis. | 2025-01-05 | 2025-01-20 | In Progress | Academic Coordinator | $3,500
Sub-task: Survey Distribution | Deploy digital surveys to all enrolled students. | 2025-01-05 | 2025-01-10 | Completed | Student Affairs Team | $800
Sub-task: Data Analysis | Analyze survey results and compile findings report. | 2025-01-13 | 2025-01-20 | In Progress | Data Analyst | $2,700
Phase 2: Curriculum Development | Design and align academic curriculum with goals. | 2025-01-21 | 2025-03-15 | Delayed | Curriculum Design Team | $8,900
Sub-task: Module Creation | Develop core modules for STEM and Humanities tracks. | 2025-01-21 | 2025-02-14 | Delayed | Subject Matter Experts | $6,300
Sub-task: Review and Approval | Submit to academic board for feedback and endorsement. | 2025-02-17 | 2025-03-15 | Delayed | Academic Review Committee | $2,600
Phase 3: Faculty Recruitment & Training | Hire qualified instructors and conduct orientation. | 2025-03-16 | 2025-04-18 | In Progress | Hiring & HR Department | $14,750
Sub-task: Recruitment Campaign | Post job openings and review applications. | 2025-03-16 | 2025-04-05 | In Progress | Hiring Team | $4,800
Sub-task: Onboarding & Training | Conduct training sessions on curriculum and pedagogy. | 2025-04-11 | 2025-04-18 | In Progress | Training Coordinator | $9,950
Phase 4: Student Enrollment & Orientation | Open enrollment and organize orientation program. | 2025-04-19 | 2025-05-16 | In Progress | Admissions Office | $7,300
Sub-task: Enrollment Drive | Launch marketing campaign and manage application process. | 2025-04-19 | 2025-05-16 | In Progress | Marketing & Admissions Team | $3,800
Phase 5: Program Launch & Evaluation | Begin academic term and establish evaluation system. | 2025-05-17 | 2026-01-31 | In Progress | Academic Director & Evaluation Unit | $18,450
Total Estimated Budget: | [5 empty] | $53,900