## Worksheet
Education Planning - Project Timeline (Financial View)
Phase | Description | Start Date | End Date | Budget Allocated ($) | Actual Spend ($) | Status
Phase 1 | Needs Assessment & Goal Setting | 2024-01-05 | 2024-01-31 | 8,500 | 7,950 | Completed
Phase 2 | College Research & Selection | 2024-02-01 | 2024-03-15 | 15,750 | 14,680 | Completed
Phase 3 | Scholarship Applications & Funding | 2024-03-16 | 2024-05-31 | 28,500 | 19,875 | In Progress
Phase 4 | Admissions & Enrollment Process | 2024-06-01 | 2024-07-31 | 35,800 | 5,432 | In Progress
Phase 5 | Financial Aid & Loan Processing | 2024-08-01 | 2024-10-31 | 47,350 | 8,965 | Delayed
Phase 6 | Moving & Orientation Preparation | 2024-11-01 | 2024-12-31 | 38,650 | 5,789 | In Progress
Total Estimated Cost: |  |  |  | 174,550 | 62,791
Project Timeline (Financial View) - Education Planning ¦ Updated as of April 2024