## Worksheet
Education Planning - Project Timeline (Large Business Style)
Phase | Activity | Start Date | End Date | Responsible Team | Status
1. Planning & Initiation | Define educational objectives and goals | 2024-01-05 | 2024-01-15 | Leadership & Strategy Team | In Progress
| Identify key stakeholders and partners | 2024-01-16 | 2024-01-31 | Project Office & External Relations | Pending
| Develop project charter and approval process | 2024-02-01 | 2024-02-15 | Governance Board | Pending
2. Design & Development | Curriculum design and review sessions | 2024-02-16 | 2024-03-31 | Academic Development Team | In Progress
| Create learning materials and digital assets | 2024-03-01 | 2024-05-15 | Content Design Team | Pending
| Prototype testing with pilot group | 2024-05-16 | 2024-06-30 | Quality Assurance & Pilot Group | Pending
3. Implementation & Rollout | Secure infrastructure and technology platforms | 2024-07-01 | 2024-07-31 | IT & Operations Team | Pending
| Train faculty and support staff | 2024-08-01 | 2024-09-15 | Human Resources & Training Unit | Pending
| Full-scale launch and enrollment phase | 2024-09-16 | 2024-10-31 | All Stakeholders | Pending
4. Evaluation & Optimization | Collect feedback from participants and staff | 2024-11-01 | 2024-11-30 | Evaluation & Analytics Team | Pending
| Analyze performance and learning outcomes | 2024-12-01 | 2024-12-31 | Data Science & Research Unit | Pending
| Final report and recommendations for future cycles | 2025-01-01 | 2025-01-31 | Executive Leadership Team | Pending
Total Duration:13 Months (January 2024 – January 2025)
Status Overview:In Progress • Pending