## Worksheet
Education Planning Project Timeline
Manager View ¦ Academic Year 2024-2025
Task ID | Task Name | Description | Start Date | End Date | Status | Owner(s)(Team Member)
#EDU-001 | Curriculum Design Phase | Develop core curriculum for Grade 9-12 subjects. | 2024-06-15 | 2024-08-31 | In Progress | Dr. Lisa Chen Math Team, Science Dept.
#EDU-002 | School Infrastructure Assessment | Evaluate classroom readiness for new academic year. | 2024-06-10 | 2024-07-15 | Completed | Marcus Williams Facilities Team
#EDU-003 | Teacher Recruitment & Onboarding | Hire and train new teaching staff. | 2024-07-01 | 2024-08-31 | In Progress | Sarah Thompson Hiring Committee, HR
#EDU-004 | Student Enrollment Campaign | Launch marketing and application process. | 2024-07-15 | 2024-10-31 | Pending | Alex Rivera Admissions Team
#EDU-005 | Technology Integration Plan | Deploy new LMS and digital learning tools. | 2024-08-15 | 2024-11-30 | Pending | Jessica Brown IT Department, Admin Team
#EDU-006 | Parent & Community Engagement Launch | Organize orientation and feedback sessions. | 2024-11-01 | 2024-12-31 | Pending | Linda Park Community Relations
#EDU-007 | Academic Year Kickoff & Training | Final staff training and first-day activities. | 2024-08-15 | 2024-09-15 | Pending | All Department Leads School Administration