## Worksheet
Education Planning - Project Timeline
Academic Year: 2024-2025 ¦ Multi-Page Template ¦ Version: 1.0
Phase | Activity | Start Date | End Date | Status | Responsible Team
Planning & Preparation | Define educational goals and outcomes | 2024-09-01 | 2024-09-15 | Pending | Academic Director, Counselors
| Develop curriculum framework and course map | 2024-09-16 | 2024-10-15 | In Progress | Curriculum Team, Faculty Leads
| Review and approve academic calendar draft | 2024-10-16 | 2024-10-31 | Pending | Administrative Council, Board of Trustees
Milestone: Academic Year Planning Complete (Target: 2024-10-31)
Resource Allocation | Identify staffing needs and hire key personnel | 2024-11-01 | 2024-12-15 | In Progress | Hiring Committee, HR Department
| Procure and distribute learning materials and equipment | 2024-11-30 | 2025-01-31 | Pending | Supply Chain, Library Team
| Secure classroom and lab facilities allocation | 2024-12-01 | 2025-01-31 | Pending | Facilities Management, Academic Coordinators
Milestone: Resources Secured (Target: 2025-01-31)
Note: This is page 1 of multiple pages. Continue to subsequent pages for Phase III and IV activities.Page 1 of 4 ¦ Confidential - For Internal Use Only
Education Planning - Project Timeline
Academic Year: 2024-2025 ¦ Multi-Page Template ¦ Version: 1.0
Phase | Activity | Start Date | End Date | Status | Responsible Team
Implementation & Delivery | Conduct teacher training and onboarding sessions | 2025-02-01 | 2025-03-15 | Pending | Hiring Committee, HR Department
| Launch academic term with orientation for students and parents | 2025-03-16 | 2025-03-31 | Pending | Student Affairs, Academic Office
| Begin semester 1 instruction and assessments | 2025-04-01 | 2025-06-30 | In Progress | All Faculty, Department Chairs
| Conduct mid-term progress reviews and feedback sessions | 2025-05-15 | 2025-06-15 | Pending | Academic Advisors, Teachers
Milestone: Semester 1 Completion (Target: 2025-06-30)
Note: Continue to next page for final phase activities and closing reports.Page 2 of 4 ¦ Confidential - For Internal Use Only
Education Planning - Project Timeline
Academic Year: 2024-2025 ¦ Multi-Page Template ¦ Version: 1.0
Phase | Activity | Start Date | End Date | Status | Responsible Team
Evaluation & Improvement | Collect student performance and feedback data | 2025-07-01 | 2025-08-15 | Pending
| Conduct faculty and staff performance reviews | 2025-07-16 | 2025-08-31 | Pending
| Review curriculum effectiveness and make revisions | 2025-08-16 | 2025-09-30 | Pending
| Prepare annual education planning report for leadership and board | 2025-10-01 | 2025-10-31 | Pending
Milestone: Annual Review Completed (Target: 2025-10-31)
Note: Final page of the multi-page timeline. This document outlines a comprehensive education planning strategy across four major phases.Page 3 of 4 ¦ Confidential - For Internal Use Only
Education Planning - Project Timeline (Summary)
Academic Year: 2024-2025 ¦ Multi-Page Template ¦ Version: 1.0
Phase | Key Objectives | Timeline (Start - End) | Status Overview
Planning & Preparation | Establish academic vision, goals, and framework | 2024-09-01 – 2024-10-31 | In Progress
Resource Allocation | Secure personnel, materials, and facilities | 2024-11-01 – 2025-01-31 | Pending
Implementation & Delivery | Launch and conduct semester 1 instruction | 2025-02-01 – 2025-06-30 | In Progress
Evaluation & Improvement | Analyze results, gather feedback, plan for next cycle | 2025-07-01 – 2025-10-31 | Pending