## Worksheet
Education Planning - Project Timeline (Office Use)
Phase | Key Activity | Start Date | End Date | Status | Responsible Person | Budget Allocation ($)(Estimated)
Preparation Phase | Needs Assessment & Goal Setting | 2024-01-05 | 2024-01-19 | Pending | Jane Smith (Coordinator) | 5,000
| Curriculum Review & Planning | 2024-01-22 | 2024-02-16 | In Progress | David Lee (Academic Lead) | 8,500
| Resource Procurement Initiation | 2024-02-19 | 2024-03-15 | Pending | Linda Chen (Procurement) | 15,000
Implementation Phase | Faculty Recruitment & Training | 2024-03-18 | 2024-05-17 | Pending | Raj Patel (HR Manager) | 18,000
| Infrastructure Setup & Equipment Installation | 2024-04-01 | 2024-06-30 | Pending | Tom Wilson (Facilities) | 35,000
| Student Enrollment & Orientation | 2024-06-15 | 2024-07-31 | Pending | Sarah Johnson (Admissions) | 7,500
Evaluation & Adjustment Phase | Mid-Term Progress Review | 2024-08-15 | 2024-08-31 | Pending | Jane Smith (Coordinator) | 3,500
| Final Evaluation & Reporting | 2024-11-01 | 2024-11-30 | Pending | Dave Lee (Evaluation Lead) | 6,500
Total Estimated Budget: | [5 empty] | 108,500