## Worksheet
Education Planning - Project Timeline (Planning View)
Phase / Task | Start Date | End Date | Status | Responsible Team | Description
Needs Assessment & Goal Setting | 2024-01-05 | 2024-01-19 | In Progress | Planning Committee | Evaluate student needs, define academic and personal goals.
Curriculum Development | 2024-01-20 | 2024-03-15 | In Progress | Academic Team | Design course structure and learning materials.
Faculty Recruitment & Training | 2024-03-16 | 2024-04-30 | In Progress | Hiring & HR Dept. | Recruit qualified educators and conduct onboarding.
Infrastructure Setup | 2024-04-01 | 2024-05-31 | Delayed | Facilities Team | Prepare classrooms, labs, and digital platforms.
Student Enrollment & Onboarding | 2024-06-01 | 2024-06-30 | Completed | Admissions Office | Admit students and prepare orientation programs.
Launch & Evaluation Cycle 1 | 2024-07-01 | 2024-08-31 | Completed | All Teams | Begin academic term and conduct first feedback review.