## Worksheet
Education Planning - Quarterly Project Timeline
Academic Year 2024-2025 ¦ Strategic Initiative for Student Success
Quarter | Project Phase | Key Activities | Responsible Department | Status | Dates (Start - End)
Q1: January - March 2025
Q1 | Planning & Assessment | Conduct student needs assessment; finalize annual education goals | Academic Affairs | In Progress | Jan 01 - Mar 31, 2025
| Curriculum Review | Review and update core curriculum for alignment with standards | Academic Department Chairs | Pending | Jan 15 - Feb 28, 2025
| Resource Allocation | Allocate funds and materials for upcoming programs | Finance & Procurement | Pending | Jan 10 - Mar 15, 2025
Q2: April - June 2025
Q2 | Program Launch | Roll out new academic support programs and tutoring initiatives | Student Success Center | Pending | Apr 01 - Jun 30, 2025
| Professional Development | Faculty training on inclusive teaching strategies and technology integration | Faculty Development Office | Pending | Apr 15 - May 20, 2025
| Mid-Year Evaluation | Assess progress and adjust strategies based on initial data collection | Educational Research Team | Pending | May 25 - Jun 10, 2025
Q3: July - September 2025
Q3 | Summer Academic Programs | Host summer bridge programs and enrichment workshops for students | Student Outreach & Engagement | Pending | Jul 01 - Sep 15, 2025
| Technology Upgrade | Implement new learning management system updates and infrastructure improvements | IT Department | Pending | Jul 10 - Aug 31, 2025
| Admissions & Enrollment Planning | Prepare for next academic year’s recruitment and course scheduling | Admissions Office | Pending | Jul 20 - Sep 20, 2025
Q4: October - December 2025
Q4 | Academic Year Review | Conduct comprehensive evaluation of program effectiveness and outcomes | Educational Research Team | Pending | Oct 01 - Nov 30, 2025
| Strategic Planning Session | Develop goals and initiatives for the following academic year | School Leadership Team | Pending | Nov 15 - Dec 10, 2025
| Reporting & Documentation | Compile final reports and present to stakeholders and board members | Office of the Provost | Pending | Dec 01 - Dec 20, 2025
Last Updated: October 15, 2024 ¦ This template is designed for quarterly tracking and reporting.