## Worksheet
Phase | Task | Start Date | End Date | Status
Planning | Educational Needs Assessment | 2024-01-15 | 2024-01-31 | In Progress
Planning | Budget Allocation Review | 2024-02-01 | 2024-02-15 | Pending
Development | Curriculum Design & Approval | 2024-02-16 | 2024-03-31 | Pending
Development | Hiring of Instructors/Trainers | 2024-03-01 | 2024-03-31 | Pending
Implementation | Student Enrollment & Registration | 2024-04-01 | 2024-05-15 | Pending
Implementation | Course Launch & Orientation | 2024-05-16 | 2024-05-31 | Pending
Evaluation | Mid-Term Feedback Collection | 2024-06-15 | 2024-06-30 | Pending
Evaluation | Final Assessment & Certification | 2024-07-15 | 2024-07-31 | Pending
Note: This timeline is subject to change based on resource availability and stakeholder feedback.