## Worksheet
Education Planning - Project Timeline (Startup Style)
Phase | Task Description | Start Date | End Date | Status
1. Research & Planning | Identify target audience and education goals. | 2024-01-05 | 2024-01-15 | In Progress
2. Curriculum Design | Develop core learning modules and course structure. | 2024-01-16 | 2024-01-31 | Pending
3. Content Creation | Produce video lectures, reading materials, and quizzes. | 2024-02-01 | 2024-03-15 | Pending
4. Platform Setup | Build and configure the learning management system. | 2024-02-15 | 2024-03-10 | Pending
5. Beta Testing | Launch pilot with a small group of students. | 2024-03-16 | 2024-04-15 | Pending
6. Feedback & Iteration | Collect feedback and improve course content. | 2024-04-16 | 2024-05-15 | Pending
7. Full Launch | Officially release the education platform to the public. | 2024-05-16 | 2024-05-31 | Pending