## Worksheet
Education Planning - Project Timeline (Summary View)
Phase | Start Date | End Date | Status | Description
Needs Assessment | 2024-01-05 | 2024-01-19 | Active | Gather student data, identify learning gaps, and assess academic goals.
Goal Setting | 2024-01-20 | 2024-01-31 | Pending | Define short-term and long-term academic objectives with student input.
Curriculum Planning | 2024-02-01 | 2024-02-15 | Pending | Select courses and learning materials aligned with goals.
Resource Allocation | 2024-02-16 | 2024-03-01 | Pending | Secure tutoring, technology, books, and other support tools.
Implementation | 2024-03-02 | 2024-11-30 | Pending | Begin executing the education plan with regular progress tracking.
Monitoring & Evaluation | 2024-04-01 | 2025-11-30 | Pending | Conduct monthly reviews, adjust strategies, and assess outcomes.
Final Review & Certification | 2025-12-01 | 2025-12-31 | Pending | Summarize achievements, document progress, and issue completion certification.