## Worksheet
Education Planning - Weekly Project Timeline
Week | Start Date | End Date | Project Phase | Description | Status | Responsible Person th>
Week 1 | 2024-04-01 | 2024-04-07 | Planning & Initiation | Define project goals, scope, and objectives. | In Progress | Dr. Alice Johnson
Week 2 | 2024-04-08 | 2024-04-14 | Curriculum Development | Develop core curriculum and learning modules. | In Progress | Prof. Michael Chen
Week 3 | 2024-04-15 | 2024-04-21 | Instructor Recruitment | Hire qualified educators and teaching assistants. | Pending | Ms. Sarah Williams
Week 4 | 2024-04-22 | 2024-04-28 | Resource Procurement | Purchase textbooks, software licenses, and lab supplies. | Pending | Mr. James Rodriguez
Week 5 | 2024-04-29 | 2024-05-05 | Infrastructure Setup | Configure classrooms, online learning platform, and labs. | Pending | Mr. Thomas Allen
Week 6 | 2024-05-06 | 2024-05-12 | Pilot Testing | Run pilot program with select students and gather feedback. | Pending | Dr. Alice Johnson
Week 7 | 2024-05-13 | 2024-05-19 | Evaluation & Refinement | Analyze pilot data and revise curriculum and delivery. | Pending | Prof. Michael Chen
Week 8 | 2024-05-20 | 2024-05-26 | Full Launch Preparation | Finalize logistics and train support staff. | Pending | Ms. Sarah Williams
Week 9 | 2024-05-27 | 2024-06-02 | Official Launch Phase | Begin full-scale delivery of educational program. | Pending | All Team Members
Week 10 | 2024-06-03 | 2024-06-09 | Evaluation & Reporting | Capture feedback and prepare progress report. | Pending | Dr. Alice Johnson