## Worksheet
Education Planning - Project Tracker (Analysis View)
Project ID | Project Name | Objective | Status | Start Date | Target End Date | Actual End Date | % Complete
PJ001 | Curriculum Development Phase 1 | Design core curriculum for Grades 9–12 | In Progress | 2024-03-01 | 2024-08-31 | — | 65%
PJ002 | Digital Learning Platform Launch | Implement LMS with interactive content delivery | Completed | 2023-11-15 | 2024-04-30 | 2024-04-25 | 100%
PJ003 | Teacher Training Program 2024 | Equip teachers with new pedagogical tools and tech skills | In Progress | 2024-05-01 | 2024-11-30 | — | 48%
PJ004 | School Infrastructure Upgrade | Renovate science labs and classrooms for modern learning | Delayed | 2024-01-15 | 2024-09-30 | — | 75%
PJ005 | Scholarship Program Rollout | Launch scholarship initiative for underprivileged students | In Progress | 2024-06-15 | 2024-12-31 | — | 35%
Total Projects |  |  | 5 | Average Completion: 59%
Analysis View ¦ Updated on April 5, 2024 ¦ Education Planning Department