## Worksheet
Education Planning - Project Tracker (Detailed Version)
Project Overview
Project Name | Curriculum Development for Secondary Education 2024-2025 |  |  | Project Manager | Dr. Amanda Richards |  | Status | In Progress
Start Date | 2024-01-15 | Target End Date | 2024-12-31 | Progress (%) | 68% |  | Budget (USD) | $450,000.00
Key Milestones & Tasks
Task ID | Task Description | Responsible Party | Start Date | Due Date | Status | Progress Details (Actual/Planned) | Notes / Dependencies
M-01 | Needs Assessment & Stakeholder Consultation | Dr. Linda Chen (Lead) | 2024-01-15 | 2024-03-31 | Completed | Completed on 2024-03-18 (98%) | Feedback from 5 regional school districts collected and analyzed.
M-02 | Curriculum Framework Drafting (Core Subjects) | Subject Teams – Math, Science, English, Social Studies | 2024-04-01 | 2024-06-30 | In Progress | 57% (Planned: 65%) - Slight delay due to staff turnover. | Math team delayed; replacement hired on 2024-05-10.
M-03 | Review & Approval by Academic Board | Academic Review Committee | 2024-07-01 | 2024-08-15 | Pending | N/A (Not started) | Requires completion of M-02 draft.
M-04 | Teacher Training Program Development | Professional Development Unit | 2024-07-15 | 2024-09-30 | Pending | N/A (Not started) | Dependent on M-03 approval.
M-05 | Field Testing in Pilot Schools (Q4) | Field Evaluation Team | 2024-10-01 | 2024-11-30 | Pending | N/A (Not started) | Pilot schools selected: 5 urban, 3 rural.
M-06 | Final Revisions & Submission for Approval | Project Manager | 2024-12-01 | 2024-12-31 | Pending | N/A (Not started) | Requires all prior milestones.
Overall Project Health & Risk Assessment | [7 empty] | Status: In Progress
Critical Risks: - Staff turnover in math team (Medium risk) - Delayed board approval (High risk) |  |  |  | Mitigation Actions: - Expedited hiring and onboarding - Weekly progress updates to board
Next Review Date
Scheduled for review on 2024-07-15. All teams to provide status updates.