## Worksheet
Project ID | Project Name | Employee Name | Role | Start Date | Expected End Date | Progress (%) | Status | Comments
PROJ-001 | Curriculum Development 2024 | John Smith | Lead Educator | 2024-01-15 | 2024-06-30 | 75 | In Progress | Final review scheduled for March 10.
PROJ-002 | Teacher Training Workshop Series | Sarah Johnson | Training Coordinator | 2024-02-01 | 2024-05-15 | 60 | In Progress | Participants registration ongoing.
PROJ-003 | School Digital Transformation Initiative | Michael Brown | IT & Education Specialist | 2024-01-20 | 2024-11-30 | 35 | In Progress | Infrastructure assessment phase underway.
PROJ-004 | Student Success Program Launch | Amanda Lee | Program Manager | 2024-03-10 | 2024-12-31 | 15 | In Progress | Planning and stakeholder meetings in progress.
PROJ-005 | Parent Engagement Initiative | Daniel Martinez | Community Outreach Officer | 2024-04-01 | 2024-11-30 | 5 | In Progress | Literature and survey design in progress.
Total Projects: | [5 empty] | 5