## Worksheet
Education Planning - Project Tracker (Extended)
Project ID | Project Name | Purpose | Start Date | Target End Date | Status | Progress (%)(Actual) | Budget (USD)(Allocated) | Spent (USD)(Actual) | Remaining Budget(Estimate) | Responsible Team | Risk Level | Key Milestones(Next 3)
PJ001 | Curriculum Development 2025 | Education Planning | Jan 15, 2025 | Jun 30, 2025 | In Progress | 48% | $125,000 | $60,000 | $65,000 | Academic Design Team | Moderate | Review Draft (Mar 1)Teacher Training Prep (Apr 15)Final Approval (May 20)
PJ002 | Digital Learning Platform Upgrade | Education Planning | Feb 1, 2025 | Sep 30, 2025 | In Progress | 67% | $350,000 | $234,500 | $115,500 | IT & E-Learning Unit | High | System Testing (Mar 28)User Feedback Loop (May 1)Go-Live Phase (Jun 30)
PJ003 | School Infrastructure Expansion | Education Planning | Jan 20, 2025 | Dec 15, 2025 | In Progress | 34% | $1,800,000 | $612,345 | $1,187,655 | Facilities Management | High | Foundation Pour (Apr 10)Roof Installation (Jul 3)Precast Panels (Sep 20)
PJ004 | Teacher Professional Development Program | Education Planning | Mar 1, 2025 | Nov 30, 2025 | In Progress | 18% | $95,000 | $17,425 | $77,575 | HR & Training Dept. | Low | Recruitment (Mar 15)Workshop Design (Apr 30)First Session (May 20)
PJ005 | Campus Sustainability Initiative | Education Planning | Feb 15, 2025 | Aug 31, 2025 | In Progress | 76% | $87,400 | $66,395 | $21,005 | Eco-Task Force | Moderate | Energy Audit (Mar 25)Solar Panel Install (Jun 10)Final Evaluation (Aug 15)
Total Overview |  |  |  |  | 4/5 in progress, 1 delayed | 47% | $2,457,400 | $990,665 | $1,466,735
Note:This tracker is updated monthly. Status indicators reflect current project health.