## Worksheet
Education Planning Project Tracker (Financial View)
Project ID | Project Name | Start Date | End Date | Budget (USD) | Actual Spend (USD) | Budget Variance (USD) | % Complete | Status | Notes
Edu-2024-001 | High School Curriculum Upgrade | Jan 15, 2024 | Jun 30, 2024 | $85,000.00 | $76,350.45 | $8,649.55 | 89% | In Progress | Textbooks and digital resources delivered ahead of schedule.
Edu-2024-002 | University Scholarships Program | Feb 1, 2024 | Dec 31, 2024 | $550,000.00 | $387,291.78 | $162,708.22 | 70% | In Progress | 54 scholarships awarded; next round selection underway.
Edu-2024-003 | Teacher Professional Development | Mar 1, 2024 | May 31, 2024 | $68,500.00 | $63,987.53 | $4,512.47 | 93% | Completed | All training sessions finalized and feedback collected.
Totals: |  |  |  | $603,500.00 | $527,629.76 | $75,870.24 | — | — | —