## Worksheet
Education Planning - Project Tracker
Project Overview
Project ID | Project Name | Start Date | End Date | Status | Budget (USD)
P001 | Curriculum Development Phase I | 2024-01-15 | 2024-06-30 | In Progress | $75,000
P002 | Teacher Training Program | 2024-03-15 | 2024-11-30 | In Progress | $95,800
P003 | Student Digital Literacy Initiative | 2024-04-15 | 2024-12-15 | In Progress | $68,500
P004 | Special Education Resources Upgrade | 2024-01-31 | 2024-10-31 | In Progress | $89,950
P005 | STEM Lab Construction | 2024-07-15 | 2024-12-31 | Pending Start | $350,000
Edit ProjectDelete Project
Task Management & Milestones
Project ID | Milestone Name | Task Description | Assignee(s) | Due Date | Status
P001 | Phase I Kickoff Meeting | Initial planning and stakeholder alignment | Alice Johnson, Mark Reed | 2024-01-31 | Completed
P001 | Subject Area Mapping | Map curriculum content to standards by subject | Dr. Sarah Williams, David Kim | 2024-03-15 | In Progress
P002 | Training Needs Assessment | Survey teachers to identify professional development needs | Linda Chen, Carlos Mendez | 2024-04-30 | In Progress
P002 | First Training Workshop | Conduct initial training session with 5 core educators | Linda Chen, Team Lead - PD | 2024-06-15 | Pending Start
P003 | Device Distribution Plan | Finalize device rollout strategy and logistics | Ryan Foster, Maya Patel | 2024-05-15 | Completed
Resource Allocation & Budget Tracker
Project ID | Budget Category | Allocated (USD) | Spent (USD) | Remaining (USD) | Utilization %
P001 | Curriculum Development Staff | $35,000 | $28,475 | $6,525 | 81%
P001 | Content Creation Tools & Software | $25,000 | $9,856 | $15,144 | 39%
P002 | Training Materials & Delivery | $45,658 | $19,783 | $25,875 | 43%
P002 | External Trainer Fees | $56,875 | $14,931 | $41,944 | 26%
P003 | Digital Devices (Laptops & Tablets) | $45,225 | $42,178 | $3,047 | 93%
Project Summary & Insights
Total Active Projects:5
On Track (Status: In Progress / Pending Start):4
Budget Utilization Rate (Overall):62%
Potential Risks:STEM Lab construction may face delays due to permitting; monitor closely.