## Worksheet
Education Planning - Project Tracker (Report Version)
Project ID | Project Name | Status | Start Date | End Date | Budget (USD) | Actual Cost (USD) | % Complete
EPR-001 | Curriculum Development Phase 1 | In Progress | 2024-01-15 | 2024-06-30 | 75,000 | 48,250 | 64%
EPR-002 | Digital Learning Platform Upgrade | On Hold | 2024-03-10 | 2024-11-30 | 150,000 | 96,750 | 64%
EPR-003 | Teacher Training Program 2024 | Completed | 2024-01-05 | 2024-12-15 | 87,500 | 87,300 | 100%
EPR-004 | School Infrastructure Assessment | In Progress | 2024-02-28 | 2024-10-31 | 55,000 | 39,850 | 72%
EPR-005 | STEM Scholarship Initiative | Planning | 2024-05-15 | 2025-12-31 | 189,000 | 7,680 | 4%
Total Projects: |  |  |  |  | 556,500 | 279,830 | 64%
Note:This report was generated on. Data reflects project status as of today.