## Worksheet
Weekly Education Planning Project Tracker
Week Start Date | Project Name | Objective/Goal | Key Activities & Tasks | Status (Current Week) | % Complete (This Week) | Progress Notes / Comments
2024-04-01 | Curriculum Development Phase I | Develop foundational course modules for Grade 8 Mathematics | - Outline core topics - Draft lesson plans - Create assessment rubrics | In Progress | 65% | Lesson plans finalized for 4 of 6 units; rubric review pending feedback.
2024-04-01 | Teacher Training Workshop | Prepare instructors for new curriculum implementation | - Schedule training sessions - Develop training materials - Confirm participant list | Completed | 100% | All 15 teachers attended the session; post-training evaluation results positive.
2024-04-01 | Resource Procurement | Acquire all required teaching materials and digital tools | - Order textbooks - Set up digital learning platform access - Verify delivery timelines | Delayed (Pending Vendor) | 40% | Textbook shipment delayed by 2 weeks due to shipping issue.
2024-04-08 | Student Assessment Design | Create formative and summative assessments aligned with new curriculum | - Draft quizzes and exams - Align questions with learning standards - Peer review content | In Progress | 50% | First draft of 3 unit assessments completed; pending validation.
2024-04-08 | Parent Communication Plan | Develop materials and strategy to inform families about curriculum changes | - Design informational flyers - Prepare parent webinar content - Distribute surveys for feedback | Completed | 100% | Flyers distributed; 92% of parents responded to initial survey.
2024-04-15 | Pilot Program Implementation | Test curriculum with one grade level in selected schools | - Select pilot schools - Train pilot teachers - Collect real-time feedback during trials | In Progress | 30% | Pilot launched in 2 out of 4 designated schools; first feedback collected.
2024-04-15 | Evaluation Framework | Establish criteria and methods to measure project success | - Define KPIs - Set up data collection tools - Develop reporting dashboard | In Progress | 75% | KPIs approved by leadership team; dashboard prototype in development.
2024-04-22 | Final Review & Approval | Complete final checks and obtain leadership sign-off on curriculum package | - Conduct final review by subject committee - Compile all materials into final package - Submit for approval | In Progress | 25% | Subject committee feedback received; revisions underway.
2024-04-29 | School Rollout Preparation | Prepare materials and training for full-scale rollout in Fall 2024 | - Finalize implementation timeline - Develop school-level support guides - Schedule regional workshops | Delayed (Pending Budget Approval) | 15% | Rollout planning paused until budget for materials is confirmed.
Weekly Summary & Forecast
Upcoming Focus (Next Week): - Complete pilot program feedback analysis - Finalize student assessment package - Resume rollout planning once budget confirmed Total Projects Active:10 ¦Status Breakdown:4 In Progress, 2 Completed, 3 Delayed, 1 On Hold