## Worksheet
Employee Management - Project Plan - Analysis View
Project Phase | Task Name | Owner | Status | Start Date | End Date | Budget (USD)
Initiation | Define Project Scope | Jane Smith | In Progress | 2024-04-01 | 2024-04-15 | $15,000.00
Planning | Resource Allocation Strategy | Mike Johnson | Not Started | 2024-04-16 | 2024-05-01 | $25,000.00
Execution | Employee Onboarding Program Design | Sarah Lee | In Progress | 2024-05-02 | 2024-06-15 | $85,000.00
Execution | Performance Review Framework Development | David Brown | In Progress | 2024-05-15 | 2024-07-31 | $68,500.00
Monitoring & Control | Monthly Performance Tracking System Implementation | Lisa Chen | Not Started | 2024-08-01 | 2024-08-31 | $35,750.00
Closure | Project Evaluation & Reporting | Jane Smith | Not Started | 2024-09-01 | 2024-09-15 | $18,350.00