## Worksheet
Employee Management Project Plan
Task ID | Task Description | Assigned To | Start Date | End Date | Status | % Complete | Dependencies
EPM-001 | Project Kickoff Meeting & Scope Definition | Project Manager | 2024-01-05 | 2024-01-12 | In Progress | 75% | -
EPM-002 | Collect Employee Data Requirements from HR & Departments | HR Analyst, Business Analysts | 2024-01-15 | 2024-01-31 | To Do | 0% | EPM-001
EPM-003 | Design Database Schema & User Interface Mockups | Systems Architect, UX Designer | 2024-02-01 | 2024-02-15 | In Progress | 60% | EPM-002
EPM-004 | Develop Core Employee Record Module (CRUD Operations) | Frontend Developer, Backend Developer | 2024-02-18 | 2024-03-15 | In Progress | 55% | EPM-003
EPM-005 | Develop Leave Management & Attendance Tracking Module | Full Stack Developer, HR Consultant | 2024-03-18 | 2024-04-15 | To Do | 0% | EPM-004, EPM-017
EPM-013 | Conduct Unit & Integration Testing | QA Team Lead, Developers | 2024-04-18 | 2024-05-15 | To Do | 0% | EPM-017, EPM-019, EPM-035
EPM-024 | Create User Manuals & Conduct Training Sessions for HR Staff | Training Specialist, Technical Writer | 2024-05-18 | 2024-06-15 | To Do | 0% | EPM-039, EPM-138
EPM-041 | Deploy Employee Management System to Production Environment | DevOps Engineer, IT Manager | 2024-06-18 | 2024-06-30 | To Do | 0% | EPM-138, EPM-199
EPM-055 | Monitor System Performance & Address Initial Issues (Post-Launch Support) | Support Team, Developers | 2024-07-01 | 2024-12-31 | To Do | 0% | EPM-199, EPM-385
PROJECT MILESTONES
M-001 | Project Kickoff Complete | PM Team | 2024-01-12 | 2024-01-15 (Target) | Closed | 100% | -
M-002 | Requirements Finalized & Approved | HR, BA Team | 2024-01-31 | 2024-01-31 (Target) | In Progress | 85% | EPM-002
M-003 | System Design Sign-off Achieved | Architect, Stakeholders | 2024-02-15 | 2024-02-15 (Target) | To Do | 0% | EPM-003
M-017 | Core Module Development Complete & Tested | Dev Team, QA Lead | 2024-03-15 | 2024-03-15 (Target) | To Do | 0% | EPM-004, EPM-179
PROJECT STATUS SUMMARY | [5 empty] | Overall Progress: 52% ¦ Next Milestone: M-002 (85%)