## Worksheet
Employee Management - Project Plan
Task ID | Task Name | Description | Assigned To | Start Date | End Date | Status
PM-001 | Hire Project Manager | Recruit and onboard a certified project manager. | Jane Smith | 2023-10-01 | 2023-10-15 | Completed
HR-002 | Recruit HR Specialist | Source and interview candidates for HR role. | Mike Johnson | 2023-10-16 | 2023-11-05 | Ongoing
IT-003 | Set Up Employee Onboarding Portal | Develop and deploy HR onboarding system. | Sarah Lee | 2023-11-06 | 2023-11-30 | Ongoing
DEV-004 | Develop Employee Dashboard | Create interactive dashboard for team performance tracking. | David Brown | 2023-12-01 | 2024-01-15 | Delayed
TRAIN-005 | Conduct Onboarding Training Sessions | Organize and deliver training for new hires. | Emily Davis | 2024-01-16 | 2024-01-31 | Completed
POLICY-006 | Finalize HR Policies & Procedures | Review, revise, and approve company-wide HR policies. | Lisa White | 2024-02-01 | 2024-03-15 | Completed
COMMS-007 | Launch Internal Communication Platform | Deploy company-wide messaging and collaboration tools. | James Wilson | 2024-03-16 | 2024-04-30 | Ongoing
EVAL-008 | Evaluate Project Outcomes & Feedback | Collect data, conduct review, and report results. | Anna Martinez | 2024-05-01 | 2024-05-31 | Completed
Total Tasks: | [5 empty] | 8
Status Summary: | [5 empty] | Completed: 4 ¦ Ongoing: 2 ¦ Delayed: 1 ¦ Not Started: 1
Generated on¦ Employee Management Project Plan - Extended Version