## Worksheet
Task ID | Task Name | Assignee | Start Date | Due Date | Status | % Complete
001 | Project Initiation | Jane Smith | 2023-10-01 | 2023-10-05 | In Progress | 75%
002 | Requirement Gathering | Mike Johnson | 2023-10-06 | 2023-10-15 | To Do | 0%
003 | Design Phase | Sarah Lee | 2023-10-16 | 2023-10-30 | In Progress | 50%
004 | Development Sprint 1 | David Chen | 2023-10-31 | 2023-11-15 | To Do | 0%
005 | Testing & QA | Linda Park | 2023-11-16 | 2023-11-30 | To Do | 0%