## Worksheet
Employee Management Project Plan
Task ID | Task Name | Assigned To | Status | Start Date | End Date | Priority
T001 | Recruitment Plan Finalization | Jane Smith | In Progress | 2024-04-01 | 2024-04-15 | High
T002 | Hiring Process Implementation | Michael Brown | To Do | 2024-04-16 | 2024-05-15 | High
T003 | New Employee Onboarding Setup | Sarah Johnson | In Progress | 2024-04-10 | 2024-05-10 | Medium
T004 | Training Program Development | David Lee | To Do | 2024-05-16 | 2024-06-30 | Medium
T005 | Performance Review System Design | Lisa Wong | In Progress | 2024-04-20 | 2024-06-15 | High
T006 | Employee Engagement Survey Launch | James Clark | To Do | 2024-06-16 | 2024-07-31 | Low
Template Type: Project Plan ¦ Purpose: Employee Management ¦ Style/Version: Home Use