## Worksheet
Employee Management Project Plan
Large Business Style - Quarterly Planning ¦ Q3 2024
# | Task Name | Responsible Team | Start Date | End Date | Duration (Days) | Progress % | Status
1 | Recruitment Strategy Development | Talent Acquisition Team | 2024-07-01 | 2024-07-15 | 15 | 98% | Completed
2 | Hiring for Senior Developers (x5) | IT Department | 2024-07-16 | 2024-08-15 | 31 | 65% | Ongoing
3 | Onboarding Program Enhancement | HR Operations | 2024-07-18 | 2024-08-10 | 24 | 75% | Ongoing
4 | Performance Review System Upgrade | HR Technology Team | 2024-07-20 | 2024-10-31 | 104 | 35% | Ongoing
5 | Talent Development Workshops (Q3) | L&D Department | 2024-08-01 | 2024-09-15 | 46 | 15% | Ongoing
6 | Diversity & Inclusion Initiative Launch | DEI Committee | 2024-08-15 | 2024-11-30 | 108 | 5% | Ongoing
7 | Employee Engagement Survey 2024 | HR Analytics Team | 2024-09-01 | 2024-09-30 | 31 | 5% | Ongoing
8 | Exit Interview Analysis & Recommendations | HR Strategy Unit | 2024-07-01 | 2024-10-15 | 107 | 85% | Completed
Project Summary:The Employee Management Project Plan for Q3 2024 focuses on strategic hiring, system upgrades, and employee engagement. As of current tracking, 35% of the overall project is complete with key milestones in progress. All tasks are assigned to dedicated teams with clear timelines and responsibilities.