## Worksheet
Employee Management - Project Plan
Project Phase | Task Description | Assigned To | Start Date | End Date | Status
Planning & Initiation | Define project scope and objectives | Jane Smith | 2024-01-05 | 2024-01-12 | In Progress
| Identify key stakeholders and team members | Mike Johnson | 2024-01-13 | 2024-01-19 | Pending
| Create initial project timeline and deliverables list | Sarah Lee | 2024-01-20 | 2024-01-26 | Not Started
Resource Allocation Summary - Phase 1
Total Team Members Assigned: |  |  | 5
Estimated Budget (Phase 1): |  |  | $45,000
Project Phase | Task Description | Assigned To | Start Date | End Date | Status
Execution & Development | Onboard new employees and conduct orientation sessions | David Brown | 2024-01-30 | 2024-02-15 | In Progress
| Implement performance review system framework | Lisa Wang | 2024-01-30 | 2024-03-15 | In Progress
| Develop employee training modules and documentation | Chris Taylor | 2024-02-16 | 2024-03-31 | Pending
| Set up HRMS integration with payroll and benefits systems | Emily Clark | 2024-03-01 | 2024-04-15 | Not Started
Monitoring and Quality Assurance Activities
Monitoring & Control | Weekly progress review meetings with project leads | Project Manager (All) | Every Monday | Ongoing | In Progress
| Milestone validation and reporting to stakeholders | Jane Smith (Lead) | 2024-03-15, 2024-04-15, etc. | Ongoing | In Progress
Project Phase | Task Description | Assigned To | Start Date | End Date | Status
Closure & Handover | Finalize employee performance tracking reports and dashboards | Lisa Wang | 2024-04-16 | 2024-05-15 | In Progress
Project Evaluation & Feedback Collection (Phase 3)
| Conduct end-of-project stakeholder feedback survey | Mike Johnson | 2024-05-16 | 2024-05-31 | Pending
Final Deliverables and Handover Summary
Project Completion Date: |  |  | 2024-06-15
Final Project Budget (Actual): |  |  | $48,750
Project Success Criteria Met: |  |  | Yes
Appendix A: Key Performance Indicators (KPIs) | Target Value | Actual Value | Status
New hire onboarding completion rate within 30 days | 95% | 93% | On Track
Employee satisfaction score (post-training) | 4.5/5.0 | 4.6/5.0 | Satisfied
System downtime during rollout period (hrs) | < 2 hrs | 1.5 hrs | Satisfied
Budget adherence percentage | ≥ 98% | 97.5% | On Track
Appendix B: Risk Register (Top 5 Risks)
Risk | Impact | Probability | Mitigation Strategy
High Priority Risks (Severity: High)
Delays in HRMS integration due to third-party dependencies | High | Medium | Dedicated vendor liaison; bi-weekly check-ins; contingency buffer of 2 weeks.
Key team member turnover during execution phase | High | Low | Cross-training plan; onboarding documentation; HR backup recruitment process.
Appendix C: Project Team & Roles
Role | Name | Email | Responsibilities
Project Leadership & Oversight
Project Manager | Jane Smith | jane.smith@company.com | Overall project planning, budgeting, reporting, and risk management.
Technical & Functional Leads
HR Systems Lead | Lisa Wang | lisa.wang@company.com | Design and implementation of performance tracking system.
Support & Integration Team
IT Integration Specialist | David Brown | david.brown@company.com | Ensure seamless integration with payroll and benefits platforms.