## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | % Complete
EML-001 | Project Kickoff Meeting | Jane Smith | 2023-10-05 | 2023-10-05 | In Progress | 100%
EML-002 | Requirements Gathering | Mike Johnson | 2023-10-06 | 2023-10-15 | In Progress | 75%
EML-003 | System Design & Architecture | Sarah Lee | 2023-10-16 | 2023-10-25 | Not Started | 0%
EML-004 | Database Development | Alex Brown | 2023-10-26 | 2023-11-15 | Not Started | 0%
EML-005 | Frontend Development | Lisa Wong | 2023-11-16 | 2023-12-10 | Not Started | 0%
EML-006 | Backend Development | Daniel Kim | 2023-11-16 | 2023-12-15 | Not Started | 0%
EML-007 | Integration Testing | Rachel Green | 2023-12-16 | 2023-12-31 | Not Started | 0%
EML-008 | User Acceptance Testing (UAT) | Tom Anderson | 2024-01-01 | 2024-01-15 | Not Started | 0%
EML-009 | Training & Documentation | Emily Davis | 2024-01-16 | 2024-01-31 | Not Started | 0%
EML-010 | Go Live & Post Implementation Review | Jane Smith | 2024-02-01 | 2024-02-15 | Pending Approval | 0%
Total Project Progress: | [5 empty] | 28%
Note:This is a one-page project plan template for the Employee Management system. All dates are subject to change based on team availability and external dependencies.