## Worksheet
Employee Management - Project Plan
Task ID | Task Description | Owner | Start Date | End Date | Status | % Complete
Onboarding Process (Q1)
E001 | Develop Onboarding Checklist | HR Manager | 2024-01-05 | 2024-01-15 | In Progress | 75%
E002 | Prepare Onboarding Materials | HR Coordinator | 2024-01-08 | 2024-01-18 | In Progress | 65%
Performance Management (Q2)
E003 | Design Performance Review Template | HR Director | 2024-04-15 | 2024-05-15 | To Do | 0%
E004 | Train Managers on Review Process | Training Specialist | 2024-05-16 | 2024-05-31 | To Do | 0%
Talent Development (Q3)
E005 | Identify High-Potential Employees | People Analyst | 2024-07-15 | 2024-07-31 | To Do | 0%
E006 | Develop Leadership Training Program | Training Manager | 2024-08-01 | 2024-11-30 | To Do | 0%
Retention Strategy (Q4)
E007 | Conduct Employee Satisfaction Survey | HR Analyst | 2024-10-15 | 2024-11-30 | To Do
Total Tasks: | [5 empty] | 7
Legend:
• In Progress: Task currently being worked on
• To Do: Task not yet started
• Completed: Task finished successfully