## Worksheet
Employee Management - Quarterly Project Plan
Q1 (Jan - Mar) | Q2 (Apr - Jun) | Q3 (Jul - Sep) | Q4 (Oct - Dec)
Key Objectives & Milestones
Onboarding Process Optimization Review current onboarding, implement digital forms, schedule training sessions. |  |  |  | Status | Owner | Due Date | Progress
| Talent Development Program Launch Create leadership curriculum, identify participants. |  |  | In Progress | Jane Smith | Apr 30 | 65%
|  | Performance Review System Update Gather feedback, revise evaluation templates. |  | Scheduled | Mike Johnson | Jul 15 | 0%
|  |  | Year-End Employee Engagement Survey Distribute, analyze results, publish findings. | Scheduled | Sarah Lee | Dec 10 | 0%
Resource Allocation & Budget Summary (Quarterly)
Q1 Budget $45,000 Allocated: $38,200 Remaining: $6,800 | Q2 Budget $52,500 Allocated: $17,350 Remaining: $35,150 | Q3 Budget $48,000 Allocated: $22,180 Remaining: $25,820 | Q4 Budget $65,000 Allocated: $9,750 Remaining: $55,250
Risk Assessment & Mitigation
Risk: Delay in onboarding system integration Mitigation: Assign dedicated IT liaison, set weekly check-ins |  |  |  | High | John Doe | Q1 Target | Ongoing
Risk: Low participation in development program Mitigation: Offer incentives, share success stories |  |  |  | Medium | Jane Smith | Q2 Target | Ongoing
Notes & Comments (for internal tracking)
- All milestones must align with company-wide DEI goals - Quarterly reviews scheduled on the first Friday of each quarter - Feedback from team leads to be incorporated into planning by the 20th of each quarter
Prepared By: HR Department ¦ Date: October 5, 2023