## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority
T001 | Hire New Marketing Manager | Jane Smith | 2024-10-01 | 2024-10-31 | In Progress | High
T002 | Onboard New Team Members | Mike Johnson | 2024-10-15 | 2024-11-30 | Not Started | Medium
T003 | Conduct Performance Reviews Q4 | Sarah Lee | 2024-11-01 | 2024-11-30 | Not Started | High
T004 | Update Employee Handbook | Linda Brown | 2024-10-10 | 2024-11-15 | In Progress | Medium
T005 | Plan Annual Retreat 2025 | Chris Wilson | 2024-11-15 | 2024-12-31 | Not Started | Low
T006 | Certify HR Compliance Training | Amy Davis | 2024-10-25 | 2024-11-10 | Completed | High
Last Updated: October 5, 2024 ¦ Prepared for Small Business Use