## Worksheet
Employee Management - Project Plan
Template Version:2.1
Project Phase | Task Description | Responsible Team Member(s) | Start Date | End Date | Status | Budget Allocated (USD)
Planning & Initiation | Define project scope and objectives for employee management system | Project Manager, HR Lead | 2024-01-05 | 2024-01-15 | In Progress | $5,000.00
Requirements Gathering | Collect input from HR and department heads on system needs | HR Analysts, IT Team | 2024-01-16 | 2024-01-30 | Pending | $7,500.00
System Design | Create wireframes and database schema for employee management tool | UX Designer, Backend Developer | 2024-01-31 | 2024-02-14 | Pending | $15,000.00
Development Phase 1 | Develop core features: user authentication and profile management | Frontend Developer, Backend Developer | 2024-02-15 | 2024-03-15 | Pending | $35,000.00
Development Phase 2 | Implement advanced HR functions: leave management and performance reviews | Full Stack Developers, QA Lead | 2024-03-16 | 2024-04-15 | Pending | $45,000.00
Testing & QA | Conduct system testing, bug fixing and user acceptance testing (UAT) | QA Team, HR Representatives | 2024-04-16 | 2024-05-15 | Pending | $25,000.00
Deployment & Training | Deploy system to production and conduct employee training sessions | IT Admin, HR Trainers | 2024-05-16 | 2024-06-15 | Pending | $30,000.00
Post-Launch Support | Provide ongoing technical support and system maintenance for 3 months post-launch | IT Support, HR Ops Team | 2024-06-16 | 2024-09-15 | Pending | $35,000.00
Total Project Budget: | [5 empty] | $237,500.00
Template Version: 2.1 ¦ Prepared on: October 5, 2024 ¦ Confidential – For Internal Use Only