## Worksheet
Employee Management - Project Timeline
Project Phase | Start Date | End Date | Status | Owner(s) | Budget Allocated ($)
Phase 1: Recruitment & Onboarding
Job Posting & Screening | 2024-04-01 | 2024-04-15 | High | Alice Johnson, HR Team | 7,500
Candidate Interviews | 2024-04-16 | 2024-04-30 | Medium | James Wilson, Hiring Manager | 5,800
Offer Extensions & Acceptance | 2024-05-01 | 2024-05-15 | Medium | Alice Johnson, HR Team | 3,750
Phase 2: Training & Integration
Orientation Program | 2024-05-16 | 2024-05-31 | Low | Lisa Chen, Training Coordinator | 9,400
Departmental Onboarding | 2024-06-01 | 2024-06-15 | Low | Team Leads, Department Heads | 7,850
Phase 3: Performance Evaluation & Growth Planning
Initial Performance Review | 2024-07-01 | 2024-07-15 | Low | Sarah Brown, HR Manager | 5,300
Development Plan Creation | 2024-07-16 | 2024-07-31 | Low | Mentors, Employees, Managers | 3,950
Note:This timeline is subject to change based on recruitment progress and organizational needs.