## Worksheet
Employee Management - Project Timeline
Project Phase | Task Name | Assigned Employee(s) | Start Date | End Date | Status
Onboarding & Planning | Recruitment Strategy Development | HR Team, Hiring Manager | 2024-06-01 | 2024-06-15 | In Progress
| Candidate Screening & Interviews | HR Coordinator, Department Leads | 2024-06-16 | 2024-07-15 | In Progress
| Offer Negotiation & Acceptance | HR Manager, Finance Representative | 2024-07-16 | 2024-07-31 | Pending
Integration & Training | Pre-Onboarding Documentation | HR Specialist, IT Admin | 2024-08-01 | 2024-08-15 | Pending
| Company Orientation Program | HR Team, Training Manager | 2024-08-16 | 2024-08-31 | Pending
| Department-Specific Training | Team Leaders, Subject Experts | 2024-09-01 | 2024-09-30 | Pending
Performance & Evaluation | 30-Day Review Meeting | Manager, HR Advisor | 2024-10-01 | 2024-10-15 | Pending
| 90-Day Performance Evaluation | Manager, HR Team, Peer Reviewers | 2024-11-01 | 2024-11-30 | Pending
| Probation Completion & Confirmation | HR Director, Senior Management | 2024-12-01 | 2024-12-31 | Pending