## Worksheet
Employee Management - Project Timeline (Client View)
Task ID | Task Description | Assigned To | Start Date | Due Date | Status | % Complete
TASK-001 | Onboarding & Orientation | Sarah Johnson (HR) | 2024-03-01 | 2024-03-15 | Completed | 100%
TASK-002 | Role Assignment & Setup | Mike Chen (Team Lead) | 2024-03-16 | 2024-03-31 | In Progress | 75%
TASK-003 | System Access & Permissions | IT Support (John Doe) | 2024-03-16 | 2024-04-15 | In Progress | 60%
TASK-004 | Training Program Completion | Lisa Patel (Training) | 2024-04-16 | 2024-05-31 | In Progress | 35%
TASK-005 | Performance Evaluation (Phase 1) | Sarah Johnson (HR) | 2024-06-01 | 2024-06-30 | Delayed | 5%
TASK-006 | Full Integration into Team Workflow | Mike Chen (Team Lead) | 2024-07-01 | 2024-07-31 | Delayed | 0%
Report Date:April 5, 2024 ¦Client View¦ Employee Management System v2.1