## Worksheet
Employee Management - Project Timeline (Data Version)
Task ID | Task Name | Assigned To | Start Date | End Date | Status | % Complete
T001 | Onboarding Preparation | HR Team | 2024-04-05 | 2024-04-15 | In Progress | 75%
T002 | IT Access Setup | IT Department | 2024-04-16 | 2024-04-18 | In Progress | 90%
T003 | Role Training Session | Department Manager | 2024-04-19 | 2024-04-21 | Pending | 0%
T004 | Performance Review Draft | HR & Manager | 2024-05-01 | 2024-05-15 | Not Started | 0%
T005 | Bonus Allocation Finalization | Finance Team | 2024-06-10 | 2024-06-15 | Not Started | 0%
This document is a data version template for Employee Management Project Timeline. Updated as of April 5, 2024.