## Worksheet
Employee Management - Project Timeline
Phase | Task | Start Date | End Date | Status | Responsible Team/Personnel | Milestones & Deliverables(Key Objectives)
Phase 1: Planning & Requirements Gathering | Define project scope and objectives | 2024-01-05 | 2024-01-15 | In Progress | Project Manager, HR Lead | Finalize project charter and stakeholder alignment document.Complete initial requirement analysis with department heads.
| Cross-functional team onboarding & role assignment | 2024-01-16 | 2024-01-31 | In Progress | HR Coordinator, IT Manager | Assign roles and responsibilities matrix.Schedule kick-off meeting with all team leads.
| Data mapping & system integration planning | 2024-02-01 | 2024-02-15 | Pending | IT Architect, Data Analysts | Map current HR systems to new platform.Create integration strategy document.
Phase 2: Design & Development | UX/UI design for employee portal | 2024-02-16 | 2024-03-15 | Pending | UI/UX Designer, Product Owner | Finalize wireframes and interactive prototype.Gather feedback from pilot users.
| Backend system configuration & module development | 2024-03-16 | 2024-05-15 | Pending | Software Developers, DBA Team | Build employee onboarding module.Develop payroll integration layer.
| Data migration script development & testing | 2024-05-16 | 2024-06-15 | Pending | Data Engineer, QA Lead | Create migration scripts for legacy employee data.Run test migrations in sandbox environment.
| Internal system integration testing (IST) | 2024-06-16 | 2024-07-15 | Pending | QA Team, IT Support | Complete end-to-end integration testing.Capture and resolve all critical bugs.
Phase 3: Testing & Validation | User Acceptance Testing (UAT) preparation | 2024-07-16 | 2024-07-31 | Pending | Project Manager, Training Team | Develop UAT test scripts and user guides.Select 50 pilot employees for testing.
| User Acceptance Testing (UAT) execution | 2024-08-01 | 2024-08-31 | Pending | Pilot Users, Support Team, HR Staff | Collect feedback and log all defects.Conduct daily sync meetings with testers.
| UAT defect resolution & final sign-off | 2024-09-01 | 2024-09-15 | Pending | Development Team, Project Sponsor | Clean up all high-priority bugs.Obtain formal sign-off from business stakeholders.
Phase 4: Deployment & Go-Live | Final environment setup and security validation | 2024-09-16 | 2024-09-30 | Pending | DevOps, Security Officer | Configure production environment.Conduct final security audit and compliance checks.
| Data cutover & go-live execution | 2024-10-01 | 2024-10-03 | Pending | IT Operations, HR Admins, Project Manager | Perform final data migration.Execute cutover with zero downtime plan.
| Post-launch monitoring & support (72-hour sprint) | 2024-10-04 | 2024-10-06 | Pending | Support Team, DevOps, HR Help Desk | Maintain 24/7 incident response.Address any urgent issues immediately.
Phase 5: Training & Adoption | Develop training content and materials | 2024-10-07 | 2024-10-15 | Pending | Training Lead, Instructional Designer | Create video tutorials, user manuals, and FAQ guides.Prepare role-specific training modules.
| Conduct employee training sessions (in-person & virtual) | 2024-10-16 | 2024-11-30 | Pending | Training Facilitators, HR Managers | Deliver 5 training sessions across departments.Capture participant feedback and ratings.
| Post-training evaluation & continuous improvement plan | 2024-12-01 | 2024-12-31 | Pending | HR Director, Project Team | Evaluate training effectiveness.Publish adoption metrics and improvement roadmap.