## Worksheet
Employee Management - Project Timeline (Freelancer Style)
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Progress (%)
T001 | Onboarding Orientation | Alice Johnson | 2024-05-15 | 2024-05-17 | In Progress | 65%
T002 | Profile Setup & Access Rights | Robert Chen | 2024-05-18 | 2024-05-19 | Pending | 10%
T003 | Initial Skill Assessment | Sophia Martinez | 2024-05-20 | 2024-05-21 | Pending | 5%
T004 | Project Kickoff Meeting | Daniel Lee | 2024-05-22 | 2024-05-23 | Pending | 0%
T005 | First Weekly Sprint Planning | Alice Johnson | 2024-05-24 | 2024-05-31 | Pending | 0%
T006 | Initial Deliverable Submission | Robert Chen | 2024-05-31 | 2024-06-03 | Pending | 0%
T007 | Performance Review (First Month) | Sophia Martinez | 2024-06-15 | 2024-06-18 | Pending | 0%