## Worksheet
Phase | Task Name | Start Date | End Date | Status | Assigned To
Planning Phase | Project Initiation & Requirements Gathering | 2023-10-01 | 2023-10-15 | In Progress | Jane Doe (PM)
| Resource Allocation & Team Assignment | 2023-10-05 | 2023-10-18 | In Progress | Mike Smith (HR)
| Timeline & Milestone Definition | 2023-10-10 | 2023-10-25 | Pending Review | Jane Doe (PM)
Design Phase | System Architecture Design | 2023-10-16 | 2023-11-05 | Pending Start | David Lee (Lead Dev)
| Development Phase | Frontend Development - UI/UX Implementation | 2023-11-06 | 2024-01-15 | Pending Start | Sarah Johnson (UI Designer)
|  | Testing Phase | Unit Testing & Code Review | 2024-01-16 | 2024-02-15 | Pending Start | Tony Wang (QA Lead)
|  |  | Deployment Phase | Staging Environment Setup | 2024-02-16 | 2024-03-15 | Pending Start | Rachel Kim (DevOps)
Post-Launch Support |  |  |  | Production Deployment & Monitoring | 2024-03-16 | 2024-04-15 | Pending Start | Rachel Kim (DevOps)
|  | Total Timeline Duration: |  |  | 2023-10-01 to 2024-04-15 | Estimated Project Completion: April 15, 2024
Phase | Start Date | End Date | Duration (Days) | Status
Planning Phase | 2023-10-01 | 2023-10-25 | 55 | In Progress (78%)
Design Phase | 2023-10-16 | 2023-11-05 | 20 | Pending Start (0%)
Development Phase | 2023-11-06 | 2024-01-15 | 71 | Pending Start (0%)
Testing Phase | 2024-01-16 | 2024-02-15 | 31 | Pending Start (0%)
Deployment Phase | 2024-02-16 | 2024-03-15 | 30 | Pending Start (0%)
Post-Launch Support | 2024-03-16 | 2024-04-15 | 31 | Pending Start (0%)
Total Project Duration: | 258 days (approx. 8.6 months) |  |  | Overall Status: On Track
Role | Name | Email | Responsibilities
Project Manager | Jane Doe | jane.doe@company.com | Overall project coordination, timeline tracking, stakeholder communication.
HR Representative | Mike Smith | mike.smith@company.com | Team assignment, employee onboarding, performance monitoring.
Lead Developer | David Lee | david.lee@company.com | System architecture, technical decisions, code quality control.
UI/UX Designer | Sarah Johnson | sarah.johnson@company.com | Interface design, user experience testing, prototyping.
QA Lead | Tony Wang | tony.wang@company.com | Test planning, test case creation, defect tracking.
DevOps Engineer | Rachel Kim | rachel.kim@company.com | CI/CD pipeline, environment management, deployment automation.
Support Specialist | James Brown | james.brown@company.com | Post-launch monitoring, incident response, user support.
Total Team Size: 7 Members ¦ Next Review Meeting: November 10, 2023