## Worksheet
Project Phase | Task Description | Responsible Employee | Start Date | End Date | Status
Planning & Setup | Define project scope and objectives | Jane Doe | 2024-04-01 | 2024-04-15 | In Progress
Hiring & Onboarding | Recruit team members and conduct onboarding sessions | Mike Johnson | 2024-04-16 | 2024-05-15 | Pending
Design Phase | Create project workflow and design documentation | Sarah Lee | 2024-05-16 | 2024-06-15 | Pending
Development Phase | Implement project deliverables and conduct testing | David Kim | 2024-06-16 | 2024-08-15 | Pending
Review & Feedback | Gather feedback from stakeholders and finalize work | Lisa Wong | 2024-08-16 | 2024-09-15 | Pending
Deployment & Training | Launch project and train end users | Raj Patel | 2024-09-16 | 2024-10-15 | Pending
Closure & Evaluation | Conduct post-project review and document lessons learned | Amanda Cruz | 2024-10-16 | 2024-10-31 | Pending
Notes:This timeline is subject to change based on project requirements and resource availability. Status updates should be reported weekly.
Last Updated: April 1, 2024 ¦ Prepared by: HR & Project Management Office