## Worksheet
Project | Employee Name | Role/Responsibility | Start Date | End Date | Status | Budget (USD)
Employee Onboarding & Integration Initiative 2024
Onboarding Phase 1 | Jane Smith | HR Coordinator | 2024-03-01 | 2024-03-15 | In Progress | $8,500
Onboarding Phase 1 | Michael Brown | IT Support Lead | 2024-03-01 | 2024-03-15 | In Progress | $9,200
Onboarding Phase 1 | Sarah Johnson | Team Manager (Dev) | 2024-03-05 | 2024-03-18 | In Progress | $11,750
Milestone: First Onboarding Batch Completed (March 15, 2024)
Onboarding Phase 2 | Daniel Lee | HR Specialist | 2024-03-16 | 2024-03-31 | Pending | $8,750
Onboarding Phase 2 | Lisa Garcia | IT Security Analyst | 2024-03-16 | 2024-03-31 | Pending | $9,500
Training & Certification | Robert Taylor | Learning & Development Lead | 2024-04-01 | 2024-05-15 | Pending | $18,300
Milestone: Full Team Integration Achieved (May 15, 2024)