## Worksheet
Employee Management - Project Timeline
Task ID | Task Description | Assigned To | Status | Start Date | End Date | Budget (USD)
T001 | Recruitment Planning | HR Department | In Progress | 2024-01-05 | 2024-01-15 | $3,500.00
T002 | Job Posting & Advertising | Marketing Team | Completed | 2024-01-16 | 2024-01-31 | $5,000.00
T003 | Candidate Screening & Interviews | HR & Hiring Managers | In Progress | 2024-02-01 | 2024-02-15 | $7,500.00
T004 | Onboarding Preparation | IT & HR Teams | Pending | 2024-02-16 | 2024-03-15 | $4,800.00
T005 | Employee Orientation & Training | Training Department | Pending | 2024-03-16 | 2024-03-31 | $6,200.00
T006 | Performance Review Setup | HR & Department Leads | Pending | 2024-04-15 | 2024-05-31 | $3,900.00
Total Project Budget | [5 empty] | $31,900.00
Prepared on:¦ Printable Version ¦ Employee Management - Project Timeline