## Worksheet
Employee Management - Project Timeline
Task ID | Task Name | Assigned To | Start Date | End Date | Status
P001 | Hiring Process Initiation | HR Team | 2023-10-01 | 2023-10-15 | In Progress
P001.1 | Job Posting Creation | HR Manager | 2023-10-01 | 2023-10-05 | Completed
P001.2 | Candidate Screening | HR Specialist | 2023-10-06 | 2023-10-10 | In Progress
P001.3 | Interview Scheduling | HR Coordinator | 2023-10-11 | 2023-10-14 | Pending
P002 | Onboarding Program Setup | HR & IT Teams | 2023-10-16 | 2023-11-30 | Pending
P002.1 | Onboarding Documentation | HR Manager | 2023-10-16 | 2023-10-25 | Pending
P002.2 | IT System Access Setup | IT Support Specialist | 2023-10-18 | 2023-10-27 | Pending
P003 | Employee Training & Development | Training Coordinator | 2023-11-01 | 2024-01-31 | Pending
P003.1 | Training Needs Assessment | HR Director | 2023-11-01 | 2023-11-07 | Pending
P003.2 | Develop Training Modules | Training Specialist | 2023-11-08 | 2023-11-30 | Pending
Total Tasks: |  |  |  | 9 | 1 In Progress, 3 Completed, 5 Pending