## Worksheet
Employee Management Project Timeline
Startup Version ¦ Q2 2024
Task ID | Task Description | Owner | Start Date | Due Date | Status | Action
#EMT-001 | Define Project Scope & Objectives | Alice Johnson | 2024-04-05 | 2024-04-12 | Completed | Edit
#EMT-002 | Design Employee Onboarding Flow | Mark Reynolds | 2024-04-13 | 2024-04-19 | In Progress | Edit
#EMT-003 | Develop HR Dashboard UI/UX | Sarah Chen | 2024-04-15 | 2024-04-30 | In Progress | Edit
#EMT-004 | Integrate Performance Tracking Module | James Wilson | 2024-04-18 | 2024-05-15 | Pending | Edit
#EMT-005 | Implement Attendance & Leave System | Lisa Park | 2024-04-22 | 2024-05-17 | Pending | Edit
#EMT-006 | Conduct User Acceptance Testing (UAT) | Tom Bradley | 2024-05-18 | 2024-06-15 | Pending | Edit
#EMT-007 | Finalize Documentation & Training Materials | Sophia Martin | 2024-06-16 | 2024-07-15 | Pending | Edit
Last updated:April 5, 2024